# Project Charter

| Project Title | Mobile Parking App | Project Manager | Cody Dangleben |
| --- | --- | --- | --- |
| Project Start Date | 8/24/2026 | Project Sponsor | Smart City Technology Initiative |
| Project End Date | 3/18/2027 |  |  |

Business Need

Drivers often spend significant time searching for available parking, leading to congestion, frustration and lost productivity. Parking operators need better tools to monitor occupancy, manage pricing, and improve utilization of parking assets for customers. The Smart City Technology has reached out for a company to accomplish a streamlined application that eases common frustrations for drivers and operators alike.

- User/Operator Registration - Parking Reservations - Payment integration and services - Live Parking availabilities - Live Operator fee updates - GPS integration - View locations - Location services - Cancel reservations - View payment history - Lot reviews - Available spaces search - Operator parking reports - Operator audits - Operator profits - User profile management - Database/backend services - Saved parking - Driver reviews - Extensive Operator dashboard - Easy Driver UI

Project Scope

- User/Operator Registration - Parking Reservations - Payment integration and services - Live Parking availabilities - Live Operator fee updates - GPS integration - View locations - Location services - Cancel reservations - View payment history - Lot reviews - Available spaces search - Operator parking reports - Operator audits - Operator profits - User profile management - Database/backend services - Saved parking - Driver reviews - Extensive Operator dashboard - Easy Driver UI

Project Scope

- User/Operator Registration - Parking Reservations - Payment integration and services - Live Parking availabilities - Live Operator fee updates - GPS integration - View locations - Location services - Cancel reservations - View payment history - Lot reviews - Available spaces search - Operator parking reports - Operator audits - Operator profits - User profile management - Database/backend services - Saved parking - Driver reviews - Extensive Operator dashboard - Easy Driver UI

- Added Construction to existing lots - Renovations - Security enforcement/services - Any surveillance additiions

Out Of Scope

- Added Construction to existing lots - Renovations - Security enforcement/services - Any surveillance

Deliverables

- Charter - SRS - Use Case Example - WBS Structure - Gantt Chart - Trello - Risk Register + Meeting Cadence - App Design blueprint - Bottom-up Cost plan - Raci Matrix - Resource Plan - User Beta launch and Testing - Mobile app finished version - Quality Report - Final App Delivery - Short/Long-Term plans for maintenance

Risks

| Risks | Mitigation Plan |
| --- | --- |

| Location inaccuracy |  | Test Location services across globe and different types of devices |  |  |
| --- | --- | --- | --- | --- |
| Payment failure |  | Use reliable company and create contingency plan |  |  |
| Excess Server Count |  | Test Load testing with performance during beta tests |  |  |
| Availability not updated |  | Implement automated refresh database system that stays up to date |  |  |
| Database not updating |  | Have a backup database server that can hold information, satellite based backup plan. |  |  |
| Beta Testing time |  | Monitor tasks completion weekly |  |  |
| App store publishing |  | Early submissions and constantly add changes |  |  |
| Beta-test Delay |  | Remain on schedule and adjust tasks amongst teams |  |  |
| Project Management changes |  | Implement a quick and effective change-process and confirm with stakeholders |  |  |
| New Stakeholder request |  | Have project safeguards in case of emergency project changes |  |  |
| High Development costs |  | Track spending, and have money reserved |  |  |
| 3rd party integration costs |  | Research and look at usage spending |  |  |
| Cloud costs |  | Optimize cloud and and related resource |  |  |
| Lack of funds |  | Detailed budget planning. |  |  |
| Lot-Developer communication issue |  | Have meetings and document requirements |  |  |
| Teams feeling overwhelmed |  | Monitor and redistribute tasks if needed |  |  |
| Miscommunication from management to team members |  | Manager meetings weekly as well as team meetings to follow up. Also, an established blue card for everyone to see |  |  |
| Users struggling to understand app features |  | Offer support services, videos, and integrated manuals to minimize confusion |  |  |
| New project members not assimilating |  | Have meetings and a dedicating program to onboarding. Establishing a shared document(s) of expectations |  |  |
| Milestones |
| project planning | start date |  | End date |
| supervision | 9/10/26 |  | 9/17/26 |
| define requirements and scope | 9/10/26 |  | 3/4/26 |
| transactions | 9/10/26 |  | 9/17/26 |
| User requirement | 9/17/26 |  | 9/24/26 |
| functional/non functional requirement | 9/24/26 |  | 10/1/26 |
| Parking space integration | 10/1/26 |  | 10/8/26 |
| Tap to pay gateway | 10/8/26 |  | 10/29/26 |
| fee calculation | 10/15/26 |  | 10/22/26 |
| Receipt system | 10/22/26 |  | 10/29/26 |
| Graphic design for Operator interface | 10/29/26 |  | 11/5/26 |
| Lot monitoring integration | 11/5/26 |  | 11/12/26 |
| Pricing management | 11/12/26 |  | 11/19/26 |
| Reservation management | 11/19/26 |  | 11/26/26 |
| App visuals | 11/26/26 |  | 12/3/26 |
| Design tests | 12/3/26 |  | 12/10/26 |
| User Login interface | 12/10/26 |  | 12/17/26 |
| User Logout interface | 12/17/26 |  | 12/24/26 |
| Payment pop up notifications | 12/24/26 |  | 12/31/26 |
| Parking reminders | 12/31/26 |  | 1/7/27 |
| Expiration notification | 1/7/27 |  | 1/14/27 |
| User registration | 1/14/27 |  | 1/21/27 |
| location services | 1/21/27 |  | 1/28/27 |
| Parking status display | 1/28/27 |  | 2/4/27 |
| Parking reservation | 2/4/27 |  | 2/11/27 |
| Payment processing | 2/11/27 |  | 2/18/27 |
| Functional services | 2/18/27 |  | 2/25/27 |
| cybersecurity | 2/25/27 |  | 3/4/27 |
| Final Version/Documentation | 3/4/27 |  | 3/11/27 |
| Project maintenance plans | 2/18/27 |  | 3/4/27 |
| Project overview and “end” | 2/25/27 |  | 3/18/27 |

Assumptions

- Budget not over - Users can access a phone and connection - Lot operators provide accurate lot information and prices - Third party services are functional across board - Cloud services are secure - Compatibility with both IOS and Android - City IT requirements are met - Approved by city

Assumptions

Financials

Bottom-Up cost plan is $100,075 based on cost estimation, Hidden costs (not included) are projected to reach over $15,000 based on cloud hosting and third-party integrations

Resource plan is $92,600

Project Team

Project Managers: Cody Dangleben, Lebron James, Kobe Bryant Project Sponsor/Approval Committee: Houston Smart City Initiative (Pending)