## Instructions
Instructions
Welcome to the GRC Tracker Pro - Risk Register Template.
Follow these steps to use this template:
1. Go to the 'Risk Register' tab.
2. Add each risk with its description, likelihood, impact, and assigned owner.
3. The 'Risk Score' will automatically calculate (Likelihood x Impact).
4. Update the Risk Status regularly to monitor progress.
5. View the Dashboard for a summary of total risks and risk score averages.

## Risk Register
Risk ID | Risk Name |  | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score (Auto) | Risk Owner | Mitigation Plan | Risk Status
Technical | Location inaccuracy |  |  | 3 | 4 | 12 | Technical Superviser | Test Location services across globe and different types of devices
Techncal | Payment failure |  |  | 3 | 5 | 15 | Backend Development team | Use reliable company and create contigency plan
Techncal | Excess Server Count |  | App and server crash | 2 | 5 | 10 | Technical Supervisor | Test Load testing with performance during beta tests
Techncal | Availability not updated |  | Parking lot data outdated | 2 | 4 | 8 | Backend Development team | Implement automated refresh database system that stays up to date
Schedule | Beta Testing time | Debugging may push development back |  | 3 | 3 | 9 | Test team | Monitor tasks completion weekly
Schedule | App store publishing |  | App needs more time to be published | 3 | 2 | 6 | App Release Manager | Early submissions and constantly add changes
Schedule | Beta-test Delay |  | Beta testing delayed due to app development team being pushed back | 4 | 2 | 8 | Technical lead | Remain on schedule and adjust tasks amongst teams
Schedule | Project Management changes |  | non functional and functional reqwuirements cahnge during cycle | 3 | 4 | 12 | Project manager | Implement a quick and effective change-process and confirm with stakeholders
Financial | HighDevelopment costs |  | Costs go beyond budget | 3 | 5 | 15 | Project Manager | Track spending, and have money reserved
Financial | 3rd party integration costs |  | Payment fees for third party are higher than expected (ex: payment integration/location services) | 3 | 3 | 9 | Financial Manager | Research and look at usage spending
Financial | Cloud costs |  | User count rises and costs for cloud storage increases | 2 | 2 | 4 | Technical Supervisor | Optimize cloud and and related resource
Financial | Lack of funds |  | Can reduce and delay timeline of project | 2 | 5 | 10 | Sponsors/Stakeholder | Detailed budget planning.
People | Lot-Developer comunication issue |  | Misunderstanding regarding lot information | 2 | 4 | 8 | Owner | Have meetings and document requirements
People | Teams feeling too much work at once |  | Project teams get overwhlemed during periods | 3 | 3 | 9 | Project Manager | Monitor and redistribute tasks if needed
People | Miscommunication from management to team |  | Expectations and constraints not properly understood and communicated on blue card | 2 | 3 | 6 | Management | Manager meetings weekly as well as team meetings to follow up. Also an established blue card for everyone to see
People | Users struggling to understand features |  |  | 3 | 2 | 6 | UI/Support team | Offer support services, videos, and integrated manuals to minimize confusion

## Dashboard
Metric | Value
Total Risks | 16
Average Risk Score | 9.1875